## Test Case
Project |  |  | banglashoppers.com |  |  |  | Test Case
Test Case Start Date |  |  | 2023-06-06
Test Case End Date |  |  | 2023-06-07 |  |  |  | PASSED | 35
Modules |  |  | User mangement |  |  |  | FAILED | 4
Test Case Execution Start Date |  |  | 2023-06-08 |  |  |  | NOT RUN | 5
Test Case Execution End Dare |  |  | 2023-06-09 |  |  |  | OUT OF SCOPE | 1
Test Case Executed By |  |  | Enisha Ashrefa |  |  |  | TOTAL | 45
Test Case Reviewed By
TC_ID | Module Name | Features | Test Type | Test Case Description | Test Data | Steps to Reproduce | Expected Result | Actual Result | Bug Screenshot | Status | Remarks/Comments
1 |  |  | Usability Testing | Browser Compatility Check | All type of browser | 1. Go to Url : https://www.banglashoppers.com/ 2. Search banglashppers.com on Browser | Should run in every browser | Works fine in all browser |  | PASSED
2 | Header | Product Browsing | Non Functional Testing (UI) | Checking font size, and color of the placeholder | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Check the search placeholder | Should be according to specification | found as per the requirements |  | PASSED
3 |  |  |  | Checking font style, spelling and grammatical errrors of the placeholder | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Check the grammatical and spelling errors of the placeholder | Should be according to specification | found as per the requirements |  | PASSED
4 |  |  |  | Verifying the alignment of each element | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Check the placement and alignment of element one by one | Should be according to specification | found as per the requirements |  | PASSED
5 |  |  |  | Verifying the search icon alignment | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Check the search icon and its placement | Should be according to specification | found as per the requirements |  | PASSED
6 |  |  |  | Verifying the mouse hover effect | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Hover the mouse on the searc h bar and see if the mouse arrow sign changes | Should change color and mouse pointer while hovering | Works as expected |  | PASSED
7 |  |  | Functional Testing | Checking the search button functionality | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Type any product to search 3. Then click on the search icon button | Should show products while clicking on the icon/button | The button doesn't work | Click here | FAILED
8 |  |  |  | Checking the the search filter | N/A | 1. Go to URL: https://www.banglashoppers.com/ 2. Type any product 3. check if it has appeared | should filter as per the typed product | filter has been done |  | PASSED
9 |  |  |  | Checking the the search filter with invalid product name | N/A | 1. Go to URL: https://www.banglashoppers.com/ 2. Type any invalid product 3. check if it has appeared | should not showcase invalid products | found as per the requirements |  | PASSED
10 |  |  |  | Verifying search recommendation | N/A | 1. Go to URL: https://www.banglashoppers.com/ 2. Start typing a product 3. check if it shows any related recommendation as of that point of typing | recommending related products | recommendation is done |  | PASSED
11 |  |  | Performance Testing | Verifying the speed of product filtering | N/A | 1. Go to URL: https://www.banglashoppers.com/ 2. Start typing a product 3. check if it shows up quickly | should appear right after typing the name | Works as expected |  | PASSED
12 |  |  | Usability Test | Sorting the relevant products | N/A | 1. Go to URL: https://www.banglashoppers.com/ 2. Start typing a product 3. check if it shows up quickly 4. Sort them | User should sort relevant product | sorts products as per users expectation |  | PASSED
13 |  | Customer Registration | UI Testing | Verifying the title of the registration form | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Clixk on the register button 3. Verify the title | Should not contain full-stop at the end of the title | Has a full-stop at the end | Click here | FAILED
14 |  |  |  | Checking color, font, style and size of each field of the form | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Verify the elements | Should appear specification wise | Found as expected |  | PASSED
15 |  |  |  | Verifying the alignment of each field | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Verify the element's alignment | Expected as specification | Found as expected |  | PASSED
16 |  |  |  | Checking the spacing between the fields | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Verify the element's gaping and spacing | Expected as specification | Found as expected |  | PASSED
17 |  |  |  | Checking the mouse hover effect | N/A | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Hover the mouse on the input field | Should change the icon while hovering mouse | Found as expected |  | PASSED
18 |  |  | Functional Testing | Verifying the email field | email@111.222.333.44444, email..email@domain.com, あいうえお@domain.com, @domain.com | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Input an invalid email 4. Input all the the other inputs valid 5. Submit the button | Should render an error message | Error message appears |  | PASSED
19 |  |  |  | Verifying the Password field | 32767 | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Input an invalid Password 4. Input all the the other inputs valid 5. Submit the button | Must Indicates to input a password combined with aphanumeric and special characters, also check the stregth | Shows message for wrong convention |  | PASSED
20 |  |  |  | Verifying the Confirm Password field | 12345678 | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Input an unmatched Password in the confirm password 4. Input all the the other inputs valid 5. Submit the button | Should not log in if the passwords don’t match | Restricts login and shows error message |  | PASSED
21 |  |  |  | Verifying the captcha field | 38z2F, 38z2 | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Input an unmatched captcha in captcha field 4. Input all the the other inputs valid 5. Submit the button | Error should occur | Error message appears |  | PASSED
22 |  |  |  | Verifying the username field | firstname: 23 lastname: 56 | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Input invalid username 4. Input all the the other inputs valid 5. Submit the button | Should not login if username contains only numeric value | Successfully creates account | click here | FAILED
23 |  |  |  | Verifying the gender field | empty field | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Keep the gender field empty 4. Input all the the other inputs valid 5. Submit the button | Should show an error message to input a gender | Doesn't show error message | Click here | FAILED | My suggesstion is not to keep the gender field empty
24 |  |  |  | Verifying the newsletter field | Check the checkbox | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Check the newsletter Checkbox 4. Input all the the other inputs valid 5. Submit the button | Should subscribe to newsletter | Does as expected |  | PASSED
25 |  |  |  | Checking existing account creation | ee@gmail.com | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Input an email that is already registered to the website witjh an account 4. Input all the the other inputs valid 5. Submit the button | Should not crteate account | Restricts creating account |  | PASSED
26 |  |  |  | Verifying fb, google login | login using fb, google | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Login using fb, google account | Should create an account using fb, google | Creates account successfully |  | PASSED
27 |  |  |  | Checking the close button | click on the close button | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register button 3. Click on the close button | Should close the form | closes the form |  | PASSED
28 |  |  | Usability Testing | Checking the redirection to log in page from register | Click on log in | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register 3. Open the form 4. Click on the log in option | form should get redirected to log in page | Log in page gets redirected |  | PASSED
29 |  |  |  | Checking user's easy log in activity |  | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register section 3.Log in with fb or google | Should create an account | Creates account successfully |  | PASSED
30 |  |  | Security Testing | Verifying password strength | 1234 | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the register section 3.Log in with password less than 8 chars 4. Input the other fields correctly | Should not get you logged in | Restricts log in |  | PASSED
31 |  |  |  | Authentication check | [5 empty] | NOT RUN
32 |  |  |  | Authorization check | [5 empty] | NOT RUN
33 |  |  |  | SQL injection check | [5 empty] | PASSED
34 |  | Log In | UI Testing | Color, font, style check |  | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the log in section | Should be as per the design | Found as expected |  | PASSED
35 |  |  |  | Verifying alignment of of each field |  | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the log in section | Alignment should be according to design | Found as expected |  | PASSED
36 |  |  |  | Mouse hover check |  | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the log in section 3. Hover the mouse on each field | Mouse arrow sign should be changed | Mouse sign changed |  | PASSED
37 |  |  |  | Active Input field checking |  | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the log in section 3. Click on the field you want to take input | Active field should be focused | As per expectation |  | PASSED
38 |  |  | Functional Testing | Email field verification | eni@gmail.com | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the log in section 3. Input wrong email 4. Input other fields correct | Should display error message | Displays error message |  | PASSED
39 |  |  |  | Verifying new member log in |  | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the log in section 3. Input wrong email 4. Input wrong password | Should not log in if not registered | found according to specification |  | PASSED
40 |  |  |  | Password check |  | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the log in section 3. Input valid email 4. Input wrong password | Should not get you logged in | Displays error message |  | NOT RUN
41 |  |  |  | Checking the forgot password option |  | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the log in section 3. Input valid email 4. Click on the forgot password option | Should redirect to a forgot password page | Redirects to the page immediately |  | PASSED
42 |  |  |  | Verifyinng the forgot password form |  | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the log in section 3. Input valid email 4. Click on the forgot password option 5. Open the form |  |  |  | NOT RUN
43 |  |  |  | Verifying fb, google login |  |  | Should log in immeditely | Logs In successfully |  | PASSED
44 |  |  |  | Verifying remember me checkbox |  | 1. Go to URL : https://www.banglashoppers.com/ 2. Click on the log in section 3. Check the remember me optiopn |  |  |  | OUT OF SCOPE | There should be a remember me checkbox
45 |  |  |  | Checking the close button | [5 empty] | NOT RUN

## Report
Test Case Report
Project Name | Banglashoppers.com
Module Name | User management
Test Case Version
Written By | Enisha Ashrefa
Executed By | Enisha Ashrefa
Reviewed By | Ehsanul Alam Sabbir
LIMITATIONS
Documents |  |  | Received | Useful
PRD |  |  | No | No
USER STORY |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Report
Bug Report
Test Case ID : #7
Test Case ID : #13
Issue | Search icon button doesn't work
| Go to URL: https://www.banglashoppers.com/ | Issue | Full-stop in title of the form
Type a product name to search
| Click on the search button | Steps to Reproduce | Go to URL: https://www.banglashoppers.com/
Steps to Reproduce |  |  | Click on the Registration form
Check the title of the form
Environment | Production | Environment | Production | Is
Severity | P4 | Severity | P9
Bug Ref. | Click here | Bug Ref. | Click here
Tested By | Enisha Ashrefa | Tested By | Enisha Ashrefa
Bug Report
Test Case ID: #22
Issue | Taking numeric values as username and creates account
Steps to Reproduce | Go to URL: https://www.banglashoppers.com/
Go to register button
Input fisrtname: 23 and lastname: 56
Input all the other fields correctly
Submit the form
Environtment | Production
Severity | P7
Bug Ref. | Click here
Tested By | Enisha Ashrefa

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (45/45)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/45)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (35/45)*100 = 87.09
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (4/45)*100 = 12.90
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/45)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A